## Financial Breakdown (hidden)
FINANCIAL BREAKDOWN FOR DEVELOPMENT OF Y-SAVE STRATEGIC PLAN 2015-2017
Phase/Key Activities |  | July W1 |  |  |  |  | Aug W1 |  |  |  |  | Aug W2 |  |  |  |  | Aug W3 |  |  |  |  | Aug W4 |  |  |  |  | Sept W1 |  |  |  |  | Sept W2 |  |  |  |  | Estimated Mandays | Responsible | Rate per Day | Amount (USD)
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
| Phase 1: Project Inception | [39 empty] | JSM | LA | DK
1 | Inception Meeting | [35 empty] | 0.5 | JSM, DK | 500 | 250 | 0.25 |  | 0.25 | bar: July W1 1
2 | Literature Review | [35 empty] | 5 | DK, LA | 500 | 2500 |  | 2.5 | 1 | bar: July W1 2 to July W1 5
3 | Discussion and Alignment with Management & Key Stakeholders | [35 empty] | 1 | JSM, LA | 500 | 500 | 0.5 | 0.5 | bar: July W1 3 to July W1 5
4 | Preparation and Submission of Inception Report | [35 empty] | 0.5 | LA | 500 | 250 |  | 0.5 | bar: Aug W1 1
Phase 2: Strategy Formulation
5 | Stakeholder Consultation | [35 empty] | 2.5 | JSM, LA | 500 | 1250 | 1.25 | 1.25 | bar: Aug W1 2 to Aug W1 4
6 | Strategic Planning Retreat - including preparation | [35 empty] | 4 | JSM, LA, DK | 500 | 2000 | 1.3333 | 1.3333 | 1.3333 | bar: Aug W1 5 to Aug W2 2
7 | Draft Strategic Plan Matrix and Outline of Strategic Plan | [35 empty] | 2.5 | JSM, LA, DK | 500 | 1250 | 0.83333 | 0.83333 | 0.83333 | bar: Aug W2 3 to Aug W3 3
Phase 3: Monitoring and Evaluation Framework
8 | Development of Monitoring and Evaluation Framework | [35 empty] | 3 | JSM, LA, DK | 500 | 1500 | 1 | 1.3333 | 1.3333 | bar: Aug W4 3 to Sept W1 2
9 | Documentation of M&E Framework | [35 empty] | 2 | LA, DK | 500 | 1000 | 0.66667 | 0.66667 | 0.66667 | bar: Sept W1 1 to Sept W1 2
Phase 3: Strategic Plan Documentation
9 | Documentation of Draft Strategic Plan | [35 empty] | 5 | JSM, LA, DK | 500 | 2500 | 1.6667 | 0.83333 | 0.83333 | bar: Aug W2 2 to Aug W4 5
10 | Review and Quality Assurance | [35 empty] | 3 | JSM, DK | 500 | 1500 | 1 | 1.6667 | 1.6667 | bar: Aug W4 3 to Sept W1 4
11 | Final Strategic Plan | [35 empty] | 1.5 | JSM, LA, DK | 500 | 750 | 0.5 | 0.5 | 0.5 | bar: Sept W1 4 to Sept W2 1
| Total | [35 empty] | 30.5 |  |  | 15250 | 9 | 11.9167 | 8.4167 | bar: Sept W1 4 to Sept W2 1
Meeting
| JSM - Dr. Jeff Sebuyira-Mukasa | July W1 3: Milestone
| LA - Louisa Akiror | July W1 3: Activity
DK - Denis Kiseka

## COG
WORK PLAN FOR THE DEVELOPMENT OF A COMMUNICATION PLAN FOR UPRS
Phase/Key Activities |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  | Duration (DAYS)
|  | WEEK |  |  |  | WEEK |  |  |  | WEEK
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1: Project Inception
1 | Contract signing & Deposit of 30% fees | [12 empty] | 1 | bar: WEEK 1
2 | Inception Meeting | [12 empty] | 1 | bar: WEEK 1
3 | Development of communication / marketing material | WEEK 1: 4 | 4
4 | Inception Report | WEEK 2: 2 | 2
Phase 2: Development Of The Campaign
5 | Conducting a search for endorsers | WEEK 2: 3 | 3
6 | Recording of endorser messages | WEEK 3: 3 | 3
7 | Creation of campaign messages | WEEK 2: 4 | 4
8 | Presentation of campaign for approval to the client | [12 empty] | 1 | bar: WEEK 3
9 | Media Buying & Booking | WEEK 2: 3 | 3
Phase 3: Execution Of The Campaign
10 | Launch of the campaign | [12 empty] | 1 | bar: WEEK 4
11 | Radio & TV Engagements | WEEK 4: 4 | 4
12 | Regional Meetings (To be footed by UPRS) | WEEK 4: 5 | 5
13 | Execution of campaign - Radio, Digital, Creative, TV | WEEK 1: 60 | 60
14 | End of Campaign | [12 empty] | 1 | bar: WEEK 4
15 | Final Report & End of Project & Payment of 30% fees | WEEK 4: 3 | 3
| Grand Total | [12 empty] | 96

## Sheet1
WORK PLAN FOR UPRS FINANCIAL YEAR 2023
Phase/Key Activities |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Status
|  | Responsibility | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project 1 | Strategic Plan for 5 years
| Project planning | UPRS MGT, UPRS BOARD | bar: 1 to 4
| Proposal writing | URSB | bar: 1 to 4
Final Draft | bar: 1 to 3
Approval | bar: 2 to 4
Implementation | bar: 1 to 4
Project 2 | Clients Engagement Campaign | Capital One Group
| Region to Region campaigns | UPRS | bar: 1 to 4
Evaluation | bar: 1 to 4
Project 3 | Stake holders engagements
| Associations and Forums meetings | Membership Committee | bar: 1 to 4; 1 to 4; 1 to 4; 1 to 4
| Partnerships and grants | PR Specialists
Project 4 | UPRS Licensing Activities
| Assessments | Licensing Department
Demand Notes | bar: 1 to 4
Cautions | bar: 1 to 4
Compliance activities
Data collection by ODK
| Enforcement | Compliance Dept | bar: 1 to 4
Internal Audits | bar: 1 to 4; 1 to 4; 1 to 4
External Audit | bar: 1 to 4
Tariff Review | bar: 1 to 4
| AGM | Management UPRS | bar: 1 to 2
Project 5 | Licensing Agent | bar: 1 to 2
| Feasibility and planning | Standby Promoters LTD | bar: 1 to 4; 1 to 2
Field rolling out
Monitoring and Evaluation | bar: 1 to 4; 1 to 4; 1 to 1
UPRS Compliance, licensing, Finance and CEO
Project 6 | Digital Collections
| Development phase | Partner in Digital Licensing | bar: 1 to 4
| Implementation | Partner in Digital Licensing | bar: 1 to 4
| Income | Partner in Digital Licensing | bar: 1 to 4
| ICT programs development | ICT, NITA-U
Project 7 | Documentation and Membership
| Sensitization | Documentation Dept
| Recruitment of members | Docuementation
Membership committees
Task 8 | Board
Full Board | bar: 1 to 4
Full Board | bar: 4 to 3
Full Board | bar: 4 to 3
Full Board | bar: 1 to 4